FLORIDA BUILDING COMMISSION 2007 WORKPLAN

REVISED FORMAT FOR 2007

1.	Recommendations for Report to 2007 Legislature

Consider preliminary recommendations to Legislature			             10/10/06

Approve recommendations to Legislature					             12/04/06

Report transmitted to Legislature						               2/08/07

2.	Panhandle Hurricane Ivan Study

Phase I

Workshop in Panhandle to review studies						9/13/05

Commission approved consensus recommendation from workshop

to conduct Panhandle windborne debris study			          10/12/05

Hire contractor to conduct Panhandle windborne debris study

Phase I	 (study initiation data development for models)			   10/05

Obtain budget amendment 							   11/05

Initiate Phase II (modify models and conduct simulations)			   12/05

Commission receives preliminary report from researchers				2/07/06

Public hearing and decide recommendation to Legislature at			2/07/06

Commission meeting

Meeting with Panhandle Building Officials						2/16/06

Recommendation to the Legislature	(In Annual Report)			            2/24/06

Contractor preliminary report presentation on study at Commission meeting	3/22/06

Contractor presentation on study at Commission meeting		  		  5/3/06

Initiate amendment of Code as directed by 2006 Legislature

Special Commission meeting for Supplemental Rule Development 		6/19/06

Workshop and contractor presentation at Destin

Supplemental Rule Development Workshop					7/11/06

Rule Adoption Hearing								8/22/06

Amendment implemented 								3/08/07

HRAC considers recommendation for Phase II					7/11/06

Commission approved proceeding with Phase II					7/11/06

Phase II

Line up funding								          8/06-9/06

Contract with UF/ARA								 12/06

Initiation reporting to HRAC								  2/07

3.	Develop Window Labeling and Default Installation Criteria

Appoint Work Group								       2/22/06

Meeting									       5/31/06

Meeting									       11/1/06

Recommendation to Code Administration TAC and Commission		       12/6/06

Code amendment submitted prior to						         1/1/07

Adopted through 2007 FBC update 			   			See Task 3

4.	Shutter and Garage Door Labeling

Work Group appointed							       8/22/06

Work Group meeting								       9/14/06

:										11/13-14/06

Report to Code Administration TAC and Commission			          12/06

Code amendments submitted for 2007 FBC by				         1/1/07

Requirements implemented through 2007 FBC				See Task 7

5.	Evaluate Termite Protection Requirements

Appoint Workgroup									3/06

Meeting									       5/17/06

Recommendations to Commission						       7/11/06

Code amendment submitted prior to 						       1/01/07

Adopted through 2007 FBC update						See Task 7

6.	Coordinate the Elevator Code and 2007 Florida Building Code updates with the Department of Business and Professional Regualtion and The Elevator Advisory Council

Initial staff meeting to establish protocols					       9/6/06

Council reviews Code amendment proposals and advises Commission	  See Task 7

7.	2007 Update to the Florida Building Code

Design of Update Process							      Apr-May 06

2006 International Codes published and available to the public			 3/1/06

Supplement version of 2006 FBC amendments available                                          9/1/06

Commission selects 2006 I Codes as foundation for 2007 FBC		           10/11/06

(Note: 2006 I Codes must be available to public for 6 months prior to selection)

Replacement pages version of 2006 FBC amendments available			11/1/06

Proposed amendments to the 2006 I Codes with Florida amendments due date	 1/1/07

Florida Specific amendment overlaps with 2006 I Codes, local amendments	 1/1/07

and 2008 FFPC correlation submitted amendments proposals by staff

Proposed amendments posted to the Web by (45 day min before TAC review)	1/15/07

45 day comment period ends								2/28/07

TACs review proposed Florida amendments, current Florida amendments

and current Local amendments and make recommendations 	       3/12-15/07

TAC recommendations posted to web (45 day min before Commission review)    4/13/07

45 day comment period ends							           5/27/07

TACs review comments and prepare public comment for Rule Workshop	     6/26&27/07

Commission considers TAC recommendations on proposed amendments

via Rule Development Workshop 					     6/26&27/07

Rule Adoption Hearing						   	          8/22/07

File Rule adopting the 2007 FBC						          9/14/07

Printed Codes available to the public						           1/1/08

Code implemented (6 months from publishing to web)			          10/1/08

Subtasks:

Joint Fire TAC/Fire Code Advisory Council review of I Codes changes to	            10/06

FFPC conducted

Meetings								10/06, 12/6/06

Correlation committee review of Florida specific amendments overlap

with 2006 I Codes							     10/06-2/07

Code books publication and printing

Provide 1st set of changes to ICC consisting of non-overlap Florida 	             		1/07

Specific changes as identified by staff

Provide 2nd set of changes to ICC consisting of changes as approved by the       	           5/27/07

TACs

Provide 3nd set of changes to ICC consisting of changes as approved by the 	          7/27/07

Commission at the Rule Workshop

# 8.	Glitch Amendments to the 2007 Florida Building Code

Printed 2007 Codes available to the public   (Note:  Code implemented 10/1/08)		1/1/08

Rule development workshop							           6/25/08

Rule adoption hearing								           8/27/08

File Rule and post Supplement to website						9/5/08

Glitch Rule effective								           9/27/08

2007 FBC effective								           10/1/08

9.	Assess Transition to IECC as Base for Florida Energy Code

Appoint Workgroup								       2/22/06

Hire Consultant to develop code comparisons					3/06

Meeting									       6/22/06

Recommendation to Commission						           7/11

Meeting									       9/14/06

Meeting									     11/15/06

Amendments proposed for 2007 FBC					        1/1/07

Energy Code revisions thru adoption and implementation of 2007 FBC	  See Task 7		Conduct workshop on energy efficiency and moisture control 		      2/28/07

10.	Amend the Florida Accessibility Code for Building Construction

Rule development workshop							      3/28/07

Rule adoption hearing if requested						        5/9/07

Rule effective									           6/07

Note:  Code amendment is only conducted to integrate current chap 553, Part II, F.S. parking requirements

11.	Revise Rule 9B-3.004 to Allow Alternates for Committee Members and Annual Amendments Process

Appoint Ad Hoc Committee							         10/11/06

Committee meeting									  12/06

Rule development workshop							               2/07

Rule adoption hearing								               4/07

Rule effective										   6/07

12.	Develop Product Validation Criteria for Methods of Demonstrating Compliance with Code

Meeting									         2/7/06

Meeting									      5/3&4/06

Meeting									         6/1/06

Recommendations to Commission						       7/11/06

Recommendations reviewed and approved by Commission			       8/22/06

Rule adoption schedule approved for amending the rule			       10/4/06

Product Approval POC review of draft rule					       1/24/07

Rule workshop								         2/7/07

Rule adoption hearing if requested						       3/28/07

Rule effective										7/07

13.	Review and Address Code Administration Needs of Local Governments and Measures to Improve Uniform and Effective Enforcement of the Code

Assessment survey									2/07

Report to Code Administration TAC						            5/07

Code Administration TAC Review and Develop Recommendations		            5/07

Recommendations to Commission						            6/07

14.	Evaluate in-home waste water recycling in coordination with Department of Health and Department of Environmental Protection

Staff investigate DOH concerns and determine statutory authorities		      10-12/06

Department of Health meeting 						        2/12/07

15.	Address implementation of the electrical systems requirements of the Energy Efficiency Code

Forum for discussion of requirements and their implementation		      7/10/06

Recommendations presented to the Commission				      7/11/06

Education and outreach

Florida Board of Professional Engineers newsletter article

Florida Engineering Society publication article			         10/06

Identification of Code enforcement and education issue by

Building Code Education and Outreach Council		       9/27/06

Add notice to Commission’s website						9/06

Send notice to all parties registered on BCIS for electrical issues		9/06

Notice Building Officials via BOAF						9/06

BOAF Education Conference Course						5/07

- Develop capability to require education for validation entities and a training program.

- Amend the 2004 FBC to eliminate wind-borne debris protection exceptions less stringent than those of the 2006 IBC and 2006 IRC

Rule adoption hearing									3/28/07

Rule effective										     6/07

18.	Develop Code-Plus criteria for insurance qualification

Determine policy direction								3/07

Contract for development								5/07

Finalize criteria								          12/07

Present in report to 2008 Legislature							2/08